## Sheet1
Name of the Supervisee |  | Chathurni Rathnayake
Student ID |  | 20220508 / w1999714
Project Title |  | COCOStat -Coconut Auction Demand Elasticity in Sri Lanka.
Meeting # | Date | Time | Discussion/Guidance given | Tasks to complete before next meeting | Next Meeting Date | Next Meeting Time | Comments on previously assigned work | Comments on progress as per plan | Supervisor sign off
1 | 15.08.2025 |  | Discussed project timeline and data collection plan. | Complete dataset collection from COCONUT DEVELOPMENT AUTHORITY / OTHER RESOURCES and begin EDA. |  |  |  |  | Fouzul Hassan
2 | 01.09.2025 |  | Reviewed data collection progress. Discussed EDA approach. | Continue EDA. Clean and preprocess the dataset. |  |  |  |  | Fouzul Hassan
3 | 17.09.2025 |  | Reviewed EDA findings. Discussed dataset cleaning steps. | Complete dataset cleaning. Prepare PPS submission draft. |  |  |  |  | Fouzul Hassan
4 | 02.10.2025 |  | Reviewed cleaned dataset. Discussed PPS submission requirements. | Revise PPS draft based on feedback. Submit PPS. |  |  |  |  | Fouzul Hassan
5 | 20.10.2025 |  | Reviewed PPS draft. Provided feedback on methodology section. | Submit PPS. Begin data ethics form. [PPS Deadline: 13/11/2025] |  |  |  |  | Fouzul Hassan
6 | 05.11.2025 |  | Discussed data ethics requirements and submission checklist. | Complete and submit data ethics form. |  |  |  |  | Fouzul Hassan
7 | 21.11.2025 |  | Reviewed ethics form draft. Suggested revisions. | Begin COCOStat analysis. |  |  |  |  | Fouzul Hassan
8 | 08.12.2025 |  | Reviewed COCOStat analysis plan. Discussed statistical methods. | Continue COCOStat analysis. Document results. |  |  |  |  | Fouzul Hassan
9 | 24.12.2025 |  | Reviewed COCOStat analysis results. Discussed findings. | Complete COCOStat analysis. Begin IPD draft. |  |  |  |  | Fouzul Hassan
10 | 09.01.2026 |  | Discussed IPD submission structure and requirements. | Continue IPD draft. Gather supporting materials. |  |  |  |  | Fouzul Hassan
11 | 26.01.2026 |  | Reviewed IPD draft. Provided feedback. | Complete and submit IPD. [IPD Deadline: 05/02/2026] |  |  |  |  | Fouzul Hassan
12 | 11.02.2026 |  | Discussed dashboard design and key metrics to visualize. | Start work on dashboard. |  |  |  |  | Fouzul Hassan
13 | 26.02.2026 |  | Reviewed dashboard progress. Suggested improvements. | Continue dashboard development. |  |  |  |  | Fouzul Hassan
14 | 13.03.2026 |  | Reviewed completed dashboard. Discussed final report outline. | Complete dashboard. Begin final report. |  |  |  |  | Fouzul Hassan
15 | 28.03.2026 |  | Reviewed final report draft. Provided final feedback. | Complete and submit Final Project Report & Code. |  |  |  |  | Fouzul Hassan